## Slide 1: NSCC Accessibility Plan Evaluation Elaine da Silva (DA) April 2025

## Slide 2: The Project

## Slide 3: Rationale
Commitment to
Accessibility & Equity
This project aligns with NSCC’s commitment to equity, inclusion, and accessibility, recognizing accessibility as a social justice issue. By evaluating the 55 commitments in the NSCC Accessibility Plan, the institution ensures compliance with the Nova Scotia Accessibility Act and the Post-Secondary Accessibility Framework.

## Slide 4: Scope
In Scope | Out of Scope
Data Collection & Validation: gathering data from department leads on accessibility initiatives (excel spreadsheet). | Creating new data sources: The project will use existing reports and stakeholder input but will not generate new data collection systems.
Data Analysis & Reporting: Analyzing qualitative and quantitative findings to identify which data is available (excel spreadsheet). | Implementing new measures: The project will provide the accessibility performance, but actual changes will be planned and executed separately.
Final Report Submission: Delivering a structured performance report based on the spreadsheet data. | Decision-making on future accessibility plans: The project will provide the report, but approval and execution of changes will be handled by NSCC leadership.

## Slide 5: Goals
Goals | Expectations | Real outcomes
Evaluate the Accessibility Plan Performance | Measure the status of the 55 commitments in the NSCC Accessibility Plan (2022-2025) | Improved Accessibility Planning
Storytelling & Insights | Develop a narrative derived from the MS Forms submissions and the Survey results from the accessibility feedback process. | No structured or reliable data to tell a story.
Promote Institutional Transparency. | Communicate findings to stakeholders to ensure accountability. | Reporting on accessibility progress

## Slide 6: Deliverables
Deliverable | Description | Planned | Realized
Project Charter | Formal document outlining the project’s goals, scope, stakeholders, and execution plan. | Feb 7, 2025 | Feb 7, 2025
Data Gather, Compilation and Analysis | Gather reports from department leads and validate data accuracy. Compiled and validated data on the 55 key commitments (spreadsheet). | Feb 14, 2025 | Feb 14, 2025
Draft Report | Report outlining findings. It includes just the data from the spreadsheet. | Feb 21, 2025 | Feb 21, 2025
Final Report | Approved and finalized version of the accessibility evaluation report. | Feb 28, 2025 | Feb 28, 2025

## Slide 7: Schedule
No. | Milestone | Completion Date
1 | Project Kickoff | Jan 31, 2025
2 | Project Charter | Feb 7, 2025
3 | Data Gather, Compilation and Analysis | Feb 14, 2025
4 | Draft Report | Feb 21, 2025
5 | Final Report | Feb 28, 2025
6 | Report adjustments (layout, color palette, filters, etc) | Apr 08, 2025

## Slide 8: Toggl Report

## Slide 9: Tools
Planned | Realized
Visio | Not used
Excel | Excel
Surveys results | Not used
Power BI | Tableau
- | Python

## Slide 10: Datasources
  Spreadsheet with the 55 commitments (raw data)

## Slide 11: Datasources
  Spreadsheet with the 55 commitments (cleaned)

## Slide 12: Events and Lessons Learned

## Slide 13: Challenges Faced
Limited data: the only source available was a spreadsheet listing 55 initiatives and some internal survey results.
Limited deadline: the final report should be delivered in three weeks.
The survey data was unstructured, expressed in free text, making it difficult to extract reliable insights in a short period of time.
The developers left the project early, discouraged by the lack of clear results.

## Slide 14: Overcoming Obstacles
After initial discomfort, I adjusted my expectations and focused on what could be done well with the available data.
I chose Tableau Public because it allows online publishing without needing a corporate account.
The project was reframed as an analysis of the accessibility plan based on the 55 commitments.

## Slide 15: Lessons Learned: hard skills
I learned to use Tableau from scratch.
I gained a better understanding of the pros and cons of Tableau vs. Power BI.

## Slide 16: Lessons Learned: soft skills
Understanding Accessibility in Nova Scotia and NSCC.
Aligning clear expectations from the beginning is essential to success.
Defining a precise scope and setting measurable criteria before initiating data analysis.
Avoid making assumptions unless they can be supported by the available data.

## Slide 17: Deliverables

## Slide 18: Project Charter

## Slide 19: Draft version in Power BI

## Slide 20: Draft version in Tableau

## Slide 21: Adjustments
The report will be inserted into a larger one (word/pdf).
It was expected to be one (maximum two) pages.

## Slide 22: Version 2 (one page)
Landscape layout
Accessible color palette (blind color)
Tableau

## Slide 23: Adjustments
Report will be printed, so dark colors should be avoided.
Portrait layout.

## Slide 24: Option 1 (original)
Option 1

## Slide 25: Option 2 (summer)
Option 2

## Slide 26: Option 3 (lightning light)
Option 3

## Slide 27: Option 4 (lightning default)
Option 4

## Slide 28: Option 5 (no color)
Option 5

## Slide 29: Word Cloud options
Built in Python
Based on the “celebrations” text file

## Slide 30: Python code

## Slide 31: What’s next?

## Slide 32: Next Steps
Develop the 2025-2028 plan using more specialized tools for project management, such as MS Planner or MS Lists.
Use this structure as a live database to create dashboards in Power BI.

## Slide 33: Thank you